## Gantt Chart 2021
Image Classification From Stratch | [22 empty] | 2021-09-20 |  |  |  |  | 2022-01-09
FYP - Cifar Image Classifier | [22 empty] | START DATE |  |  |  |  | END DATE
Task ID | Task Name | Start Date | End Date | Duration (Weeks) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
T01 | Research appropriate features & models that can realistically be delivered within the time and focus on a iterative approach to their implementations | 2021-09-20 | 2021-10-03 | 2 | bar: 1 to 2
T02 | Research the CIFAR-10 dataset necessary tools for development | 2021-09-20 | 2021-10-03 | 2 | bar: 1 to 2
T03 | Initial project setup, python venv dependencies and source control. Implementation methods for reading CIFAR dataset. First iteration of core algorithms i.e. convolution. | 2021-09-20 | 2021-10-03 | 2 | bar: 1 to 2
T04 | Simple feature extraction i.e. greyscale and colour histogram | 2021-10-04 | 2021-10-10 | 1 | bar: 3
T05 | Feature extraction techniques sobel edges and colour histogram | 2021-10-04 | 2021-10-10 | 1 | bar: 3
T06 | Simple model (KNN) development (concurrent along side T04) | 2021-10-04 | 2021-10-17 | 2 | bar: 3 to 4
T07 | Evaluate techniques developed using naive metrics such as accuracy to gather baseline results with different features | 2021-10-11 | 2021-10-17 | 1 | bar: 4
T08 | Advanced feature extraction techniques HOG RnD. Implement HOG and test with KNN agasinst other features. Also work on HOG visualization to prove the algoritm works as expected | 2021-10-18 | 2021-10-31 | 2 | bar: 5 to 6
T09 | Review current state of the program, refactor to ensure consistency of code, ensure adequate test coverage. Normalise CIFAR-10 on load. | 2021-11-01 | 2021-11-07 | 1 | bar: 7
T10 | Research Logistic Regression implementation approach. Look at common LR python class structures such as Keras | 2021-11-01 | 2021-11-14 | 2 | bar: 7 to 8
T11 | Design class for LR ensuring the class shares simlarities (black box) with KNN classifier. Each model should be interchange to aid testing and evaluation. | 2021-11-08 | 2021-11-28 | 3 | bar: 8 to 10
T12 | Logistic regression models require a lot of time to train. Work on persisting the models to file | 2021-11-22 | 2021-11-28 | 1 | bar: 10
T13 | Project cleanup fix issues with HOG visual at cell level. Cleanup comments in code. Work on UI implementation add PyQt5 support to the project and confirm matplotlib support in PyQt5 | 2021-11-29 | 2021-12-05 | 1 | bar: 11
T14 | Metrics. Work on the initial implementation and tests for metrics for both binar and multiclass. Work on Confusion matrix generation ROC curve, thresholds and run these features against logistic regression model. | 2021-11-29 | 2021-12-12 | 2 | bar: 11 to 12
T15 | Exams. Continue project reasearch focusing particularly on CNN implementation for the new year. Along with SIFT implementation (after researching) SIFT appears to be better for matching images rather than determining images though I would still like to implement it given it is more challenging. | 2021-12-13 | 2021-12-26 | 2 | bar: 13 to 14
T16 | Implentation of SIFT following David Lowe's original paper. Also implement Canny Edge extraction algorithm for comparison with sobel | 2021-12-27 | 2022-01-09 | 2 | bar: 15 to 16
T17 | Design API for CNN and update convolution algorithm, if possible optimize and also add stride paramter. | 2022-01-03 | 2022-01-09 | 1 | bar: 16
T18 | Prepare Interim demo of FYP Demo confirmed for 12/1/22 | 2022-01-03 | 2022-01-09 | 1 | bar: 16

## Gantt Chart 2022
Image Classification From Stratch | [22 empty] | 2022-01-10 |  |  |  |  | 2022-04-06
FYP - Cifar Image Classifier | [22 empty] | START DATE |  |  |  |  | END DATE
Task ID | Task Name | Start Date | End Date | Duration (Weeks) | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43
T19 | Further preparation for FYP interim demostration. Conduct FYP demo | 2022-01-10 | 2022-01-16 | 1 | bar: 17
T20 | Review of the codebase. Do all features developed still have a place in the project? Is there common functionality in features that could be extracted into seprate units. Are there any aspects of the project which are not functioning and are contributing to technical debt. | 2022-01-17 | 2022-01-30 | 2 | bar: 18 to 19
T21 | Futher research into CNN particularly back propagration and whether the existing gradient decsent is applicable to CNN, does this cause a refactor of LR classifier | 2022-01-17 | 2022-01-23 | 1 | bar: 18
T22 | Further work on Metrics code is necessary as there seems to be issues with metrics in multiclass runs with LR | 2022-01-24 | 2022-01-30 | 1 | bar: 19
T23 | CNN implementation, along with comparisions to LR models and metrics, exploring different features and experimenting with different layers | 2022-01-24 | 2022-03-06 | 6 | bar: 19 to 24
T24 | Begin dissertation. Research format of dissertation along with information from CSC-3002. Project Introduction and background information on CIFAR | 2022-02-07 | 2022-03-06 | 4 | bar: 21 to 24
T25 | Review of the current system focusing on UI and UX test coverage | 2022-01-31 | 2022-02-13 | 2 | bar: 20 to 21
T26 | UI development. By this point I imagine UI will be the most lacking aspect of the system. Adding as a task to allow for further development time if necessary | 2022-02-07 | 2022-02-20 | 2 | bar: 21 to 22
T27 | Review of feature extraction methods. Are they robust. Can they be visualized in a meaningful way that demostrates that the implementations work. Can FE methods be tweaked via UI parameters, can they be optimised. Review of models can they be evalutated in a way which lends itself to comparison in the dissertation. Are metrics on par with expected results from researched experiments? | 2022-02-21 | 2022-03-06 | 2 | bar: 23 to 24
T28 | Continue the dissertation to the end of the project. Submission 1st April | 2022-03-07 | 2022-03-27 | 3 | bar: 25 to 27
T29 | Possible development time, should bugs / issues arise whilst writing the report. | 2022-03-07 | 2022-03-27 | 3 | bar: 25 to 27
T30 | Prepartion of the demo video. Obtain video for early parts of the system on a continual basis. Submission 6th April | 2022-02-07 | 2022-03-27 | 7 | bar: 22 to 27
T31 | Final Week and Submission | 2022-03-28 | 2022-04-10 | 2 | bar: 28 to 29

## ©
© TemplateLab.com